TECHNICAL PROPOSAL

Patroni-based PostgreSQL High Availability & Disaster Recovery Platform

Patroni-based HA Cluster with Cross-Site DR on-premises

Prepared for: [Client Name] Prepared by: Mahmoud Gamal Date: 8/5/2026 Version: 2.0 — Revised for Submission

IMPORTANT — Please confirm before work begins: This proposal is built on a 10-server (5 HA + 5 DR) interpretation of the client’s request. The original Scope of Work states “install and configure PostgreSQL on five servers” and a total of 100 man-days, which could alternatively be read as a single 5-node cluster with no cross-site DR. This distinction materially changes cost, timeline, and architecture and must be confirmed in writing before this proposal is finalized. See Section 5 (Assumptions & Open Questions) for the full explanation.

1. Executive Summary

This proposal outlines the design and implementation approach for a highly available, disaster-resilient PostgreSQL database platform. The solution is built on open-source enterprise technologies — PostgreSQL, Patroni, and etcd — orchestrated to provide automatic failover within the primary site and a geographically separated Disaster Recovery site.

The engagement covers architecture design, end-to-end implementation, connectivity and load balancing, backup and point-in-time recovery, monitoring, security hardening, disaster recovery setup, and documentation with knowledge transfer. The total effort is estimated at 100 man-days, delivered in a hybrid model (primarily on-site, with a smaller remote-work component).

A small number of scope items depend on information not yet confirmed by the client (see Section 5 — Assumptions & Open Questions). This proposal presents the recommended architecture based on current understanding and will be finalized once those points are confirmed.

Compliance Statement

This proposal complies with the requirements set out in the client’s Scope of Work document, with the exceptions and clarifications noted in Section 5 (Assumptions & Open Questions). A full requirements traceability matrix is provided in Appendix A, indicating Full / Partial / Not-in-Core-Scope compliance status for each stated requirement.

2. Proposed Architecture

The proposed solution consists of two geographically separated on-premises sites: a Primary Site (HQ) and a Disaster Recovery Site (DR). Each site hosts a Patroni-managed PostgreSQL cluster, where the HQ site operates as the primary production cluster and the DR site operates as a standby recovery cluster.

- Primary Site (HQ) – Five PostgreSQL servers running PostgreSQL, Patroni, and a 5-member etcd cluster. The cluster operates with one Primary node and four Replica nodes, providing automatic failover, replication management, and high availability within the primary data center.

- Disaster Recovery Site (DR) – Five PostgreSQL servers running PostgreSQL, Patroni, and a 5-member etcd cluster, configured as a Patroni Standby Cluster. The DR cluster continuously receives streaming replication from the HQ Primary Site and remains in standby mode until a disaster recovery activation is required.

- Connectivity Layer – Client applications connect through a dedicated HAProxy layer. HAProxy continuously monitors the Patroni REST API and automatically routes database connections to the current Primary node. For high availability of the connectivity layer, a Virtual IP (VIP) managed by Keepalived (or an equivalent customer-provided load balancing solution) is recommended.

- Backup & Monitoring – Database backups will be managed using pgBackRest, with backup data stored in the customer’s existing backup repository or enterprise backup solution. A dedicated monitoring server running Prometheus, Grafana, and Alertmanager will provide health monitoring, alerting, and performance dashboards for PostgreSQL, Patroni, etcd, and the underlying operating systems.

2.1 High-Level Diagram

PostgreSQL HA/DR Architecture

Figure 1: HQ (Primary Site) and DR (Secondary Site) each run a 5-node PostgreSQL + Patroni + etcd cluster. Applications connect via HAProxy/VIP to the HQ cluster; the DR cluster streams continuously from HQ and is promoted only via a manual, documented runbook.

2.2 Why This Design

- Automatic failover inside the Primary Site — if any PostgreSQL node fails, Patroni promotes a replica within seconds, with no manual intervention.

- Protection against a full-site or region failure — the DR site holds a continuously updated copy of the data in a separate Secondary Datacenter.

- HAProxy + Virtual IP (VIP) for traffic routing, or an existing enterprise load-balancing solution. If the customer already owns an enterprise load balancer, the proposed HAProxy layer can be replaced without changing the database architecture.

- Controlled DR activation — cross-site promotion is intentionally manual to avoid split-brain risk; a documented runbook governs the activation procedure.

3. Scope of Work

3.1 Core Scope (Included in the 100 Man-Day Estimate)

| Work Item | Description |
| --- | --- |
| Architecture & Design | Finalize topology, network design, and configuration standards for both sites. |
| PostgreSQL Installation | Install and configure PostgreSQL on all 10 servers (5 HA + 5 DR). |
| Patroni & etcd (HA) | Deploy Patroni and a 5-member etcd cluster for the Primary Site; validate automatic failover. |
| Patroni Standby Cluster (DR) | Configure the DR site as a Patroni standby cluster streaming from the Primary Site, with its own 5-member etcd cluster supporting controlled failover operations. |
| Connectivity / Load Balancing | Implement HAProxy with Patroni REST API health checks and VIP management using Keepalived, or integrate with an existing enterprise load balancer if available. |
| Backup & PITR | pgBackRest configured with existing backup solution as the repository; encrypted backups (AES-256); WAL archiving for point-in-time recovery; validated restore procedure. |
| Monitoring & Alerting | Prometheus + Grafana + Alertmanager on a dedicated monitoring VM; metrics from Patroni, PostgreSQL, etcd, and OS-level exporters, covering availability, replication lag, disk usage, checkpoints, sessions, and backup status. |
| Security Hardening | TLS between nodes, restricted pg_hba rules, SCRAM-SHA-256 authentication, role-based access control, OS-level hardening, firewall rules. |
| Audit Logging | pgAudit extension configured for DDL, role, and write-statement logging. |
| Maintenance & Patching | Rolling-restart procedure for minor version upgrades and OS patching, coordinated through Patroni with no full-cluster downtime. |
| DR Runbooks | Documented, tested procedures for DR promotion and eventual failback. |
| Documentation & Knowledge Transfer | Full architecture and operations documentation, plus a knowledge-transfer session with the client’s team. |

3.2 Optional / Add-On Items (Not in Core Scope)

The following items are excluded from the core 100 man-day estimate, consistent with how they are categorized in the client’s original request document. They can be scoped and quoted separately if required:

- Data Migration — migrating data from an existing/legacy database, if one exists. Effort cannot be estimated until the source system is confirmed.

- Performance Benchmarking — formal load testing (e.g., pgbench) and a documented performance report.

- Infrastructure Automation (Terraform) — available on request if the client wants infrastructure-as-code for provisioning.

- PgBouncer Connection Pooling — recommended only if expected concurrent application connections are high; to be confirmed based on expected application load.

- 24x7 Managed Support — ongoing operational support beyond go-live stabilization; can be quoted as a follow-on support contract (see Section 10 for proposed SLA framework).

4. Technical Approach — Key Design Decisions

4.1 High Availability (Primary Site)

Patroni manages PostgreSQL lifecycle and automatic promotion; etcd (5 members) provides distributed consensus and leader election.

Validated in testing: failover from a stopped primary to a newly promoted leader completes within seconds, with replicas resynchronizing automatically once the failed node returns.

4.2 Disaster Recovery (Cross-Site)

The DR site streams continuously from the Primary Site’s Load Balancer endpoint, so it remains correctly targeted even through Primary Site failovers.

DR promotion is a manual, documented action — never automatic — to eliminate split-brain risk. The DR site maintains its own 5-member Patroni and etcd cluster to support controlled failover operations. DR activation is subject to the change-approval process defined in Section 9 (Governance & Project Management), given its status as a privileged, high-impact action.

4.2a Replication Policy (Synchronous vs. Asynchronous)

- Within the HQ site (Primary to local replicas): proposed as synchronous (or synchronous with quorum) to guarantee zero data loss on local failover.

- Across sites (HQ to DR): proposed as asynchronous, given the WAN latency between geographically separated sites — synchronous replication over a cross-site link would add write latency to every transaction on the Primary.

This split policy (synchronous locally, asynchronous cross-site) is standard Patroni practice and balances performance with resilience. Final policy is subject to client confirmation of acceptable data-loss tolerance (RPO) for a full site-loss event.

4.3 Backup & Recovery

pgBackRest with the customer’s existing/enterprise backup repository. Backups are encrypted at rest (AES-256), consistent with the scope’s data protection requirements.

Proposed retention: full backups weekly (4-week retention), continuous WAL archiving (7-day retention) — subject to the client’s compliance requirements.

Restore procedure will be tested and documented, with actual RTO measured and recorded.

4.4 Monitoring

Single monitoring VM hosting Prometheus, Grafana, and Alertmanager.

Metrics sources: Patroni’s built-in /metrics endpoint, postgres_exporter, node_exporter (per VM), and etcd’s native metrics.

Dashboards and alerts will cover, as required by the scope:

- Cluster/node availability and current role (Primary/Replica) per node

- Replication lag (bytes and time) for each replica and the DR standby cluster

- Disk usage and growth trend per node (data directory, WAL directory)

- Checkpoint frequency and duration

- Active session counts, connection saturation, and long-running queries

- Backup job status (success/failure, last successful backup timestamp, WAL archiving status)

- etcd cluster health and quorum status

4.5 Security

TLS encryption will be configured for PostgreSQL client and cluster communication where applicable.

Role-Based Access Control — PostgreSQL roles will be structured following least-privilege principles, with separate roles for application access, DBA/administrative access, read-only reporting access, and monitoring/exporter access. Role grants will be scoped to specific databases/schemas rather than superuser-equivalent access wherever possible.

Credential & Secret Handling — Database credentials and service account passwords will not be stored in plaintext configuration files where avoidable. Where the client has an existing secrets management solution (e.g., HashiCorp Vault, cloud KMS), integration will be scoped separately; otherwise, credentials will be managed via restricted-permission configuration files with OS-level access controls, and SCRAM-SHA-256 password hashing will be enforced.

pgAudit enabled for DDL, role, and write-statement auditing, with CSV-formatted logs.

Centralized log aggregation (e.g., Grafana Loki) is an open item to be finalized in a later phase.

4.6 RPO / RTO Targets

| Scenario | Target RPO | Target RTO | Notes |
| --- | --- | --- | --- |
| Single node failure at HQ (local failover) | Near-zero (seconds) | < 60 seconds | Automatic Patroni promotion; no data loss under synchronous local replication |
| Primary node corruption at HQ | Near-zero to seconds | 1–5 minutes | Depends on detection + promotion time |
| Loss of one DR node | N/A (no failover triggered) | N/A | Cluster continues with reduced DR redundancy; remediation during next maintenance window |
| Loss of HQ site (DR activation) | Seconds to minutes (depends on async cross-site replication lag at time of failure) | 30–60 minutes (manual, approval-gated activation) | Actual RTO will be measured and documented during DR failover testing (Phase 8) |
| Recovery of HQ after DR event (failback) | N/A | To be determined based on data resynchronization volume | Estimate will be finalized after first DR test |

These are provisional target figures based on the proposed architecture. Final RPO/RTO commitments will be validated and documented during the HA/DR failover testing phase (Phase 8) and confirmed in the DR runbook.

4.7 Maintenance & Patching

Minor version upgrades and OS patching will be performed using a rolling restart approach coordinated through Patroni: replicas are patched and restarted first (one at a time, confirming healthy rejoin before proceeding), followed by a controlled switchover of the Primary role and patching of the former Primary. This approach maintains cluster availability throughout the maintenance window with only a brief (single-digit second) interruption during the final switchover.

Maintenance windows will be scheduled and communicated in advance per the change control process (Section 9). Major version upgrades are treated as a separate, individually-scoped activity requiring dedicated testing and a documented rollback plan.

5. Assumptions & Open Questions

The following points materially affect the architecture, effort, and timeline, and require client confirmation before the proposal can be finalized:

- Cluster Topology — this proposal assumes the 10 servers are split as 5 (HA) + 5 (DR) across two sites. An alternative reading of the request (“install PostgreSQL on ten servers”) could mean a single 5-node cluster in one location with no cross-site DR. This choice significantly changes the architecture, resilience profile, and effort — please confirm in writing.

- DR Site Location — if the split-site model is confirmed, please confirm the target region/datacenter for the DR site.

- Platform — this proposal assumes the platform is on-premises.

- Data Migration — please confirm whether an existing/legacy database must be migrated, and if so, its type and approximate size.

- Cross-Site Failover Mode — this proposal assumes DR activation is manual (operator-initiated) rather than automatic. Please confirm this is the desired behavior.

- Replication RPO Tolerance — needed to finalize the synchronous/asynchronous replication policy described in Section 4.2a.

- Expected Connection Load — needed to determine whether PgBouncer should be added to the architecture.

- Server Count Flexibility — please confirm whether the 5-server count (per site) is fixed, or whether an additional VM (e.g., for PgBouncer) could be added if required.

- Secrets Management — please confirm whether an existing secrets management platform (e.g., Vault, cloud KMS) should be integrated, per Section 4.5.

6. Proposed Timeline

The following phase breakdown totals the agreed 100 man-days. Actual calendar duration depends on the agreed weekly schedule (85% on-site / 15% remote) and will be confirmed once the start date is set.

| Phase | Description | Man-Days |
| --- | --- | --- |
| 1 | Architecture finalization & environment prep | 10 |
| 2 | HA cluster build (PostgreSQL + Patroni + etcd, 5 nodes) | 20 |
| 3 | Connectivity layer (HAProxy, health probes) | 10 |
| 4 | DR site build (standby cluster, cross-site replication) | 20 |
| 5 | Backup & PITR (pgBackRest + Backup Solution) | 10 |
| 6 | Monitoring & alerting | 10 |
| 7 | Security hardening, TLS, audit logging | 10 |
| 8 | HA/DR failover testing & validation | 5 |
| 9 | Documentation & knowledge transfer | 5 |

7. Deliverables

- A production-ready PostgreSQL HA cluster (5 nodes) in HQ with automatic local failover.

- A configured DR standby cluster (5 nodes) with documented promotion and failback procedures.

- HAProxy configuration providing transparent primary routing for applications.

- Automated backup and point-in-time recovery, with a validated and documented restore procedure.

- A monitoring and alerting stack (Prometheus, Grafana, Alertmanager) covering all nodes and services.

- Security hardening (TLS, pgAudit, RBAC, restricted access rules) applied across all nodes.

- Complete architecture and operations documentation.

- A knowledge-transfer session with the client’s technical team.

8. (Reserved)

(Section number reserved to preserve alignment with original proposal numbering; content consolidated into Sections 9–11 below.)

9. Governance & Project Management

Status Reporting — A weekly project status report will be issued covering progress against the phase plan, open risks, pending decisions/approvals needed from the client, and completed/upcoming activities.

Escalation Process — A named project lead and technical lead will be assigned as primary points of contact. An escalation path will be defined for issues not resolved at the working level within [X business hours], escalating to [vendor account/engagement manager]. (Names and escalation SLA hours to be finalized before contract signature.)

Change Management — Any change to agreed architecture, scope, or man-day allocation will be documented as a formal change request, including impact on cost and timeline, and will require client sign-off before implementation. DR activation and other privileged/high-impact actions during operations are subject to the same approval discipline.

Review Gates — The engagement includes formal review/sign-off checkpoints at:

- Architecture design approval (end of Phase 1)

- HA cluster build validation (end of Phase 2)

- DR site and failover test completion (end of Phase 8)

- Production readiness sign-off prior to go-live

10. Operational Support Model & SLAs

The core 100 man-day engagement covers implementation and go-live stabilization. Ongoing 24x7 managed support is excluded from core scope (Section 3.2) and can be quoted separately as a follow-on support contract. The response targets below apply to that optional support offering, aligned with the client’s stated severity framework:

| Severity | Business Impact | Target Response | Vendor Commitment |
| --- | --- | --- | --- |
| Critical | Production outage or severe data service disruption | 10–20 minutes | Workaround / restoration target |
| High | Major degradation or replication issue | 30 minutes – 1 hour | Workaround / restoration target |
| Medium | Non-critical issue affecting operations | 2 hours | Resolution target |
| Low | Minor issue or request | 4 hours | Resolution target |

During the engagement itself (pre-go-live and the early-life stabilization period), issues will be triaged and addressed as part of the active project team’s daily engagement, following the same severity classifications above on a best-effort basis ahead of a formal support contract being in place.

11. Vendor Qualifications

(Placeholder structure — to be completed with actual company/team detail before sending to client.)

- Relevant Experience — [Summary of PostgreSQL/Patroni HA-DR implementation experience: number of similar engagements, industries served.]

- Engineering Team — [Qualifications/certifications of assigned PostgreSQL and Linux engineers.]

- Customer References — [At least three references of similar size/complexity, with contact permission — name, industry, scope delivered.]

- Training & Support Capability — [Description of documentation standards, knowledge-transfer approach, and post-go-live support capability.]

- Go-Live & Stabilization Support — [Confirm ability to provide hypercare/stabilization coverage immediately following go-live.]

- Engineered Solutions Capability — [Confirm experience supporting vendor-engineered/appliance-based platforms, if applicable to this client’s environment.]

12. Next Steps

- Review and confirm the open items in Section 5 (Assumptions & Open Questions).

- Finalize the architecture diagram and man-day allocation based on the client’s answers.

- Agree on a start date and finalize the phase schedule.

- Sign off on this proposal to begin Phase 1.

Appendix A — Requirements Traceability / Compliance Matrix

| Scope Requirement | Status | Reference |
| --- | --- | --- |
| Design and document Patroni target architecture | Full | Section 2 |
| Install/configure PostgreSQL on five servers | Partial — proposal assumes 10 (5 HA + 5 DR); pending confirmation | Section 5 |
| Install/configure Patroni + distributed config store | Full | Sections 3.1, 4.1 |
| Replication, failover, switchover controls | Full | Sections 4.1, 4.2 |
| Connectivity services (HAProxy/PgBouncer/VIP) | Full (HAProxy+VIP); PgBouncer optional/conditional | Sections 3.1, 3.2 |
| Backup, restore, WAL retention, PITR | Full | Section 4.3 |
| Health monitoring, alerting, dashboards, log visibility | Full | Section 4.4 |
| Security hardening, certs, access controls, audit logging | Full | Section 4.5 |
| Failover, DR, restore, rollback runbooks | Full | Sections 3.1, 4.2 |
| Admin knowledge transfer and documentation | Full | Sections 3.1, 7 |
| Migration of existing DBs/apps | Not in Core Scope | Section 3.2 |
| Performance benchmarking and optimization | Not in Core Scope | Section 3.2 |
| 24x7 managed support | Not in Core Scope | Sections 3.2, 10 |
| Infrastructure automation | Not in Core Scope (available on request) | Section 3.2 |
| Extended retention backup repo / object storage integration | Not addressed — clarify with client if needed | — |
| Engineered platform support | Not addressed — depends on client’s environment | Section 11 |
| HA: automatic failure detection/election/restoration | Full | Section 4.1 |
| Replication: sync/async policy defined | Full | Section 4.2a |
| PITR: validated restore workflow | Full | Section 4.3 |
| Maintenance: controlled patching/rolling restart | Full | Section 4.7 |
| Connectivity: stable client redirection | Full | Sections 3.1, 4.1 |
| Observability: named metrics (lag, disk, checkpoints, sessions, backup status) | Full | Section 4.4 |
| Security: RBAC, TLS, encryption, secret handling, audit | Full | Section 4.5 |
| DR: RPO/RTO assumptions + activation runbook | Full | Section 4.6 |
| DR: recovery of HQ after DR event, downtime estimate | Partial — approach defined, downtime estimate pending first DR test | Section 4.6 |
| Governance: weekly status reports | Full | Section 9 |
| Governance: escalation process + named contacts | Full — contacts to be named before signature | Section 9 |
| Governance: change management process | Full | Section 9 |
| Governance: formal review gates | Full | Section 9 |
| Support/SLA requirements (severity table) | Full — applies to optional support contract | Section 10 |
| Vendor qualifications | Full — details to be completed | Section 11 |